## Sheet1
Risk Management Table
Risk Summary | Risk Category | Probability | Impact(1-4) | RMMM
Poor Quality of documentation | BU | 15% | 1 | If any topic is missing in documentation then we will discussed and add it into the documentation.
Quality assurance, Speed of the software | TI | 20% | 2 | The quality of software is must batter, each of the module of software can communicate properly with each other.
Delivery Deadline | BU | 25% | 2 | The cost associated with a late delivery is critical. Step have been taken based on scope of project delivery deadline.
Size in line of codes | Product size | 25% | 3 | Increasing in the size of the code increase the software size.
Lake of database stability | TI | 35% | 2 | The possible errors are come due to poor error checking.These issues should be brought to the attention of each of the members that are contact with the database.
Change in requirement | PS | 30% | 2 | This insures that the product we are producing, and the requirements of the customer are equivalent.
Software interface | TE | 20% | 1 | Software that enables it to continue operating reliably on interface.
Technology to be built new for developer | TE | 25% | 2 | If the technology is new for organization than it’s a Catastrophic impact, the developer have to learn that technology very quickly.